## Sheet1
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project | SHOULD HAVE | Dependency | Nivash S | 3- Completed
S1 | S1 | US-001 | Anlaysis of project overview & environmental setup | MUST HAVE | Dependency | Nivash S | 3-Completed
S2 | S2 | US-002 | Learned about cybertools(nmap,shodan,virustotal,nessus,openvas) | MUST HAVE | nmap,shodan,virustotal,nessus,openvas | Nivash S | 3- Completed
S2 | S2 | US-002 | Analysis of 4 layer in the project | SHOULD HAVE | Dependency | Nivash S | 3- Completed
S3 | S3 | US-003 | learn about Layer 3:Risk Scoring &Analysis | SHOULD HAVE | ChatGpt | Nivash S | 3- Completed
S3 | S3 | US-003 | Working on flow and document creation | MUST HAVE | Dependency | Nivash S | 3- Completed
S4 | S4 | US-004 | Analysis of vulnerability by implementing cvss score,exploitation | MUST HAVE | Dependency | Nivash S | 3- Completed
S5 | S5 | US-005 | Working to develop code to get desired output for exploitation and prediction | MUST HAVE | EPSS AND 30 DAY PREDICTION | Nivash S | 3- Completed
S6 | S6 | US-006 | Merge the modules of layer 3 into single code | MUST HAVE | Shodan,Virustotal,Nessus | Nivash S | 3- Completed
S6 | S6 | US-006 | Making report for the desired code and doing test cases | MUST HAVE | Dependency | Nivash S | 3- Completed
S7 | S7 | US-007 | Developing Documentation of desired and research report | COULD HAVE | Ms word | Nivash S | 3- Completed
S7 | S7 | US-007 | Development of PPT work | SHOULD HAVE | Ms PowerPoint | Nivash S | 3- Completed
S8 | S8 | US-008 | Final Demonstration and adding files into GitHub repo | MUST HAVE | GitHub,VS code | Nivash S | progress